## NCR Report
NCR: March
Site | NCR resolved beyond 21 days |  |  | NCR open beyond 21 days |  |  | Total
| Civil Finishing | MEP | Structure | Civil Finishing | MEP | Structure
External Development | 0 | 0 | 0 | 0 | 0 | 0 | 0
Veridia- Tower 01 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Veridia- Tower 02 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Veridia- Tower 03 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Veridia- Tower 04 | 1 | 1 | 3 | 1 | 0 | 1 | 7
Veridia- Tower 05 | 5 | 1 | 8 | 1 | 0 | 1 | 16
Veridia- Tower 06 | 0 | 0 | 0 | 0 | 0 | 1 | 1
Veridia- Tower 07 | 0 | 2 | 12 | 0 | 0 | 0 | 14
Veridia-Club | 0 | 0 | 0 | 0 | 0 | 0 | 0
Veridia-Commercial | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Structure_and_Finishing
Project | Tower Name | Structure | Finishing
Eden | Tower4 | 4% | 0%
Eden | Tower6 | 4% | 0%
Eden | Tower7 | 3% | 0%
Eden | Tower5 | 1% | 0%
Veridia | Tower 4 Finishing | 0% | 87%
Veridia | Tower 5 Finishing | 0% | 20%
Eligo | Tower G Finishing | 0% | 3%
Eligo | Tower H Finishing | 0% | 0%
EWS | EWST1 | 62% | 0%
EWS | EWST2 | 0% | 0%
EWS | EWST3 | 0% | 0%
LIG | LIGT1 | 0% | 0%
LIG | LIGT2 | 0% | 0%
LIG | LIGT3 | 42% | 0%
Eligo | T(F) | 0% | 0%
Eligo | T(G) | 41% | 0%
Eligo | T(H) | 100% | 0%
Veridia | T2 | 20% | 0%
Veridia | T3 | 51% | 0%
Veridia | T4 | 100% | 0%
Veridia | T5 | 100% | 0%

## Safety report
Safety: Current Month
Site | No. of Safety NCRs open beyond 7 days
Common_Area | 24
External Development | 0
Veridia-Club | 0
Veridia-Commercial | 0
Veridia-Tower01 | 19
Veridia-Tower02 | 10
Veridia-Tower03 | 5
Veridia-Tower04 | 4
Veridia-Tower05 | 5
Veridia-Tower06 | 1
Veridia-Tower07 | 3

## House Keeping NCR REport
Housekeeping: Current Month
Site | No. of Housekeeping NCRs open beyond 7 days
Common_Area | 3
External Development | 0
Veridia-Club | 0
Veridia-Commercial | 0
Veridia-Tower01 | 3
Veridia-Tower02 | 3
Veridia-Tower03 | 1
Veridia-Tower04 | 0
Veridia-Tower05 | 0
Veridia-Tower06 | 0
Veridia-Tower07 | 0

## Activity
Activity Name | Apr | May | Jun | Total Count
C-EL-Third Fix | 3 | 4 | 0 | 7
C-ELV-Third Fix | 2 | 5 | 0 | 7
C-F-Final Fix | 2 | 3 | 0 | 5
C-P-Final Fix | 0 | 4 | 0 | 4
C-Painting first coat | 8 | 0 | 0 | 8
C-Stone cladding | 4 | 0 | 0 | 4
CP-Final Fix | 138 | 14 | 0 | 152
Counter stone works | 9 | 0 | 0 | 9
EL-Third Fix | 34 | 6 | 0 | 40
Glass Installation | 60 | 16 | 0 | 76
Grouting of tiles major area | 28 | 0 | 0 | 28
Grouting of toilets & balcony Tiles | 1 | 1 | 0 | 2
HV-Final Fix | 15 | 4 | 0 | 19
Installation of Windows | 1 | 0 | 0 | 1
Installation of wardrobes and cabinets | 8 | 0 | 0 | 8
MS staircase glass railing | 32 | 0 | 0 | 32
Paint in balcony and shafts | 4 | 2 | 1 | 7
Painting final coat | 14 | 0 | 0 | 14
SS Framing | 44 | 8 | 0 | 52
Splash pool and deck installation | 28 | 4 | 0 | 32
Steam shower cubicle fixing | 28 | 4 | 0 | 32
UP-Final Fix | 31 | 6 | 0 | 37